## Sheet1
# | Feature | Milestone | Side | Priority | Status | Why we need it | Depends on
F1 | Entity-Component system | Foundation | Engine | Done | Built | Everything in the game is an entity with attachable components. | -
F2 | Transform + scene graph (parenting) | Foundation | Engine | Done | Built | Positions/rotations in 3D; parenting drives the chase camera. | F1
F3 | Camera component + separate Game view | Foundation | Engine | Done | Built | Renders the player view through an in-scene camera entity. | F1
F4 | Lua scripting (on_start/update/destroy) | Foundation | Engine | Done | Built | All gameplay behavior is written as scripts, hooked per frame. | F1
F5 | Input API (key_down / key_pressed) | Foundation | Engine | Done | Built | Scripts read the keyboard, gated so UI typing never leaks in. | F4
F6 | Deferred spawn / destroy queues | Foundation | Engine | Done | Built | Safely create/remove entities mid-update (bullets, kills). | F1
F7 | Scene save/load + node editor | Foundation | Engine | Done | Built | Author levels as JSON; build logic visually into Lua. | F4
1 | Quaternion orientation for entities | M1 Fly the jet | Engine | Must | Done | Jets pitch/yaw/roll freely in full 3D; euler angles gimbal-lock and tumble. | F2
2 | Move-along-local-forward API | M1 Fly the jet | Both | Must | Done | A jet flies the direction it faces, not along fixed world axes. | 1
3 | Vector / quaternion math in Lua | M1 Fly the jet | Engine | Must | Done | forward/up/right, rotate, translate_local, look_at exposed to scripts. | 1
4 | Flight control script (pitch/yaw/roll/throttle) | M1 Fly the jet | Scripting | Must | Done | Maps input to rotation and thrust; the feel of flying. | 2, 3
P | Arcade flight physics (energy model) | M1 Fly the jet | Scripting | Should | Done | Airspeed from thrust/drag/gravity; climb and dive trade speed for altitude, with stall. Pure Lua, no engine feature needed. | 4
5 | Smoothed chase camera | M1 Fly the jet | Both | Should | Done | Camera eases behind the jet and looks at it; readable flight. | F3
6 | Mouse-look / aim input | M1 Fly the jet | Engine | Should | Todo | Steering with keys alone is stiff; mouse delta feels natural. | F5
7 | Tag / layer on entities | M2 Weapons & hits | Engine | Must | Done | Marks player/enemy/bullet so hits and AI target by category, not name. | F1
8 | scene.find / nearest in Lua | M2 Weapons & hits | Engine | Must | Done | Scripts locate the player and the nearest tagged target each frame. | 7
9 | Distance / sphere-overlap check | M2 Weapons & hits | Engine | Must | Done | scene.nearest(tag,pos,radius) - cheap collision, no physics engine. | 8
10 | Generic projectile spawn | M2 Weapons & hits | Engine | Must | Done | scene.spawn places an entity facing a direction, running a script. | 2
11 | Health / damage system | M2 Weapons & hits | Both | Must | Done | HealthComponent + scene.damage; targets die at zero HP. | 9
12 | Script properties in Inspector | M2 Weapons & hits | Engine | Should | Done | Tune speed/health/fire-rate per entity without editing code. | F4
13 | Enemy AI scripts (chase / evade / attack) | M3 Enemies | Scripting | Must | Done | Makes targets fight back; scripting once find + move + math exist. | 4, 8
14 | Spawner / wave system | M3 Enemies | Scripting | Should | Done | Populates the sky and ground with waves of targets. | 10
15 | Ground vehicles (ground-bound AI) | M3 Enemies | Scripting | Should | Todo | A second, slower target type adds variety to objectives. | 13
16 | HUD / 2D overlay on Game view | M4 Presentation | Engine | Must | Done | Crosshair, health and target markers - can't aim or read state without them. | F3
17 | Model loading (.glb / .obj) | M4 Presentation | Engine | Should | Done | Real jet and vehicle models instead of cubes - the biggest visual leap. | F1
18 | Skybox | M4 Presentation | Engine | Should | Done | Flying in a black void reads as broken; a sky gives horizon and orientation. | -
19 | Ground / terrain plane | M4 Presentation | Both | Should | Done | Somewhere for ground vehicles, and a reference for altitude and speed. | -
20 | Explosion / particle effect | M4 Presentation | Engine | Nice | Todo | Kill feedback; makes destroying things satisfying. | 11
21 | Audio (engine, guns, explosions) | M4 Presentation | Engine | Should | Todo | A huge feel multiplier; raylib has audio built in. | -
22 | Script hot-reload | M4 Presentation | Engine | Should | Partial | Tweak flight/AI scripts live without a rebuild - big dev-speed win. Partial: the Inspector has a manual Reload button; there is no automatic reload when the file changes on disk. | F4
23 | Game state (menu / play / win / lose / restart) | M5 Game loop | Both | Must | Done | Turns a sandbox into a game with a real start and end. | 11
24 | Score / objectives | M5 Game loop | Scripting | Should | Done | A goal to play toward: destroy N targets, survive a timer. | 23
25 | Main menu / UI screens | M5 Game loop | Engine | Nice | Todo | Start screen, restart and settings - the shell around the loop. | 23
26 | Collider shapes (Sphere / Box / Capsule) | M6 Physics | Engine | Must | Done | Collision volumes with a local offset and rotation, sized in the Inspector. Replaces the sphere-only hitbox and is the per-body shape a physics engine needs. | 9
27 | Jolt integration (PhysicsWorld + RigidBody) | M6 Physics | Engine | Must | Todo | Adds the Jolt library, one physics body per Collider+RigidBody, stepped each frame with transforms synced back. Dynamic mode: physics moves the bodies, scripts no longer set positions directly. | 26
28 | Forces API for Lua (force / torque / impulse / velocity) | M6 Physics | Engine | Must | Todo | Scripts push bodies instead of teleporting them - the only way gameplay can drive dynamic physics. | 27
29 | Flight model rewritten as forces | M6 Physics | Scripting | Must | Todo | Thrust, lift and drag become real forces on the jet body. The hardest step: prototype early, because it decides whether flying still feels right. | 28
30 | Collision damage + raycast bullets | M6 Physics | Both | Must | Todo | A contact listener turns real collisions into damage, and bullets become raycasts so a fast shot cannot pass through a target between two frames. Retires the distance-based hit test. | 27
31 | Terrain heightfield collider (ground / crash) | M6 Physics | Engine | Should | Todo | Makes the ground solid, so flying into it crashes instead of passing through. | 27, 19
32 | Compound colliders + parented body sync | M6 Physics | Engine | Should | Todo | Several colliders under one body, for shapes a single primitive cannot cover, plus a world-to-local bridge so a parented dynamic body behaves. | 27
33 | Directional lighting + shading | M4 Presentation | Engine | Should | Done | Terrain and models currently render flat and unlit; one directional light plus a shader gives them form and depth. | 17
F8 | Data-flow visual scripting (typed pins, variables, codegen) | Foundation | Engine | Should | Built | A full Blueprints-style node language that generates Lua: typed pins, variables, params, branches and loops. Grew out of F7; every gameplay script has been reproduced as a graph. | F7